Subcontract Best Practice

1.	Prepare a tracking system to monitor the invoice amounts, dates, and cumulative total

2.	Prepare a tracking system for technical reports due from the subcontractor

3.	Prepare a tracking system for required cost share from the subcontractor

4.	Review of invoice upon receipt by department:

a)	Are invoiced expenses in line with the approved budget?

b)	Is the current invoice total correct?

c)	Is the cumulative amount less than or equal to the subcontract total?

d)	Has the contractor submitted technical reports to support expenditures?

e)   If required in contract, have financial reports been provided?

e)	Is the required cost share reported on the invoice?

5.	Processing of invoice by department:

a)	Update departmental records, summary sheets, etc.

b)	Write subaward index and expense account code on invoice.

c)	Principal Investigator indicates approval on invoice by original signature.

d)	Forward invoice to OSP-CAU.

f)    OSP-CAU forwards to A/P for processing.

6. 	Before final payment processing:

a)	Technical report submitted or enclosed?

b)	Patent reports submitted or enclosed?

c)	Property reports submitted or enclosed?

d)	Closing authorization from subcontractor?

e)	Cost sharing requirement met?